## owssvr (10)
Task Name | Description | Due Date | Subcommittee | Task Status | Priority | Status for Reporting Comments
CMLD Deployment (Phase1)-04B | Industry Outreach - working with NERC MMWG on data management processes |  | Load Modeling Working Group (LMWG) | In Progress | (1) High | IN PROGRESS - NERC LMTF presented and discussed CMLD model and data management processes at NERC MMWG meeting in March of 2019 and 2020. Ultimate goal is to make CMLD available in 2021 MMWG series of cases
CMLD Deployment (Phase1)-05 | Field Test |  | Load Modeling Working Group (LMWG) | In Progress | (1) High | IN PROGRESS - NERC Regional Entities, Planning Coordinators and Transmission Planners are performing CMLD field test to make a decision on their CMLD deployment plans. Recent Benchmarking results have shown critical parameter changes and would require ano
CMLD Deployment (Phase1)-06 | Regional Support |  | Load Modeling Working Group (LMWG) | In Progress | (1) High | NERC LMWG to work with Regions to develop support and feedback structure with CMLD deployment
CMLD Deployment (Phase2)-13 | Load Composition Analysis |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal | On-going effort to improve our understanding of load composition
CMLD Deployment (Phase2)-14 | Dynamic Load Monitoring |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal | Deployment of dynamic data records in distribution substations and commercial buildings for purpose of load monitoring. DOE will provide resources to support data analysis
CMLD Deployment (Phase2)-15 | Coordination with SPIDERWG |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal | Coordinate with SPIDERWG on DER modeling for dynamic load model, ensure that SPRIDERWG-develop models and data sets are updated in Load Model Data Tool
CMLD Deployment (Phase2)-17 | System Event Benchmarking |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal | Encourage entities to benchmark actual events with the composite load model and report to the group
C2-Reliability Guideline: Communication and Coordination Strategies for Transmission Entities and Distribution Entities regarding Distributed Energy Resources | Develop recommended strategies to encourage coordination between Transmission and Distribution entities on issues related to DER such as information sharing, performance requirements, DER settings, etc. |  | System Planning Impacts from Distributed Energy Resources Working Group Coordination (SPIDERWG-COORDINATION) | On Hold | (2) Normal | Tabled to align with standards review (C6 activity) activity.
C5-SPIDERWG Terminology: Working Definitions Document | Review of existing definitions and terminology and development and coordination of new terms, for consistent reference across sub-groups. |  | System Planning Impacts from Distributed Energy Resources Working Group Studies (SPIDERWG-STUDIES) | In Progress | (2) Normal | Initial draft complete; will update RSTC as necessary. Subsequent revisions will be explored by team, as needed.
C7-Tracking and Reporting DER Growth | Coordinated review of information regarding DER growth, including types of DER, size of DER, etc. Consideration for useful tracking techniques for modeling and reliability studies. |  | System Planning Impacts from Distributed Energy Resources Working Group Studies (SPIDERWG-STUDIES) | In Progress | (2) Normal | In monitoring and data collection stage.
3-IEEE p2800 Monitoring and Support | Monitor and support the activities of IEEE p2800, and provide technical expertise and input as requested. |  | Inverter-Based Resource Performance Working Group (IRPWG) | In Progress | (2) Normal | Ongoing, as needed.
6-Seasonal Assessment Improvements | Assist RAS with incorporation of probabilistic metrics in the RAS seasonal reports |  | Probabilistic Assessment Working Group (PAWG) | In Progress | (2) Normal | New work plan item based on ERO-RAPA and RAS discussion. Joint effort with RAS following RAS schedule
PRC-019 Implementation Guidance | PRC-019 Implementation Guidance |  | System Protection and Control Working Group (SPCWG) | In Progress | (2) Normal
Protection System Commissioning Lessons-Learned | Errors in protection design documents and/or failure to employ effective commissioning testing practices can lead to protection system misoperations. SPCS will review and revise (as necessary) the 2014 lessons-learned document and conduct industry outreach to increase awareness of the revised lessons-learned. |  | System Protection and Control Working Group (SPCWG) | In Progress | (2) Normal
Inverter-based Resources Impacts to BPS Protection Systems | Inverter-based Resources Impacts to BPS Protection Systems Transmission protection practices and systems will need to adapt to the changing nature of the grid. SPCS will develop a technical report on the impacts that BPS-connected inverter-based resources can and are having on BPS protection systems. The report will be coordinated with NERC Inverter-Based Resources Performance Working Group (IRPWG), as needed, to bring protection and inverter experts together. The intent of the technical report is to provide a framework, roadmap, and technical guidance for industry to tackle this challenge. |  | System Protection and Control Working Group (SPCWG) | In Progress | (2) Normal
PRC-024-3 Implementation Guidance | Due to changes in PRC-024-3 the Implementation Guidance will require updating to help entities demonstrate compliance with the revised standard. |  | System Protection and Control Working Group (SPCWG) | In Progress | (2) Normal
Develop a Data Reporting Instruction for entities to collect and report GIC and magnetometer data as specified in the ROP Section 1600 Data Request | Develop a Data Reporting Instruction for entities to collect and report GIC and magnetometer data as specified in the ROP Section 1600 Data Request |  | Geomagnetic Disturbance Task Force (GMDTF) | Completed | (2) Normal | DRI is complete. PC Reviewed January 14 – February 14, 2020. NERC IT staff is developing the data reporting application for implementation before year-end 2020. Update to RSTC is on Sept agenda. Disband upon completon of work in 2020. ORS activities suppo
Analyze data from GMD events collected under the GMD Data Request and other necessary information to further understand GIC effects on BES facilities. Summarize observations, including observations on GIC modeling. | Analyze data from GMD events collected under the GMD Data Request and other necessary information to further understand GIC effects on BES facilities. Summarize observations, including observations on GIC modeling. |  | Geomagnetic Disturbance Task Force (GMDTF) | In Progress | (2) Normal | Activity is from 2018 RISC Report. The required reviews are enabled through the implementation of the Sect 1600 data request occurring in 2020. RTOS activities support ongoing monitoring and reduction of GMD risk.
Protection considerations for information traditionally shared between entities (modeling, load-flow, one-lines) | Perhaps a joint effort with OC? |  | Security Working Group (SWG) | In Progress | (2) Normal
Security or implementation guidance for cloud-based EAMS and PAMS | In support of CIP development efforts pertaining to virtualization issues |  | Security Working Group (SWG) | In Progress | (2) Normal
Examine high risk violations for implementation guidance opportunities | CIWG can identify opportunities but may leverage Cyber or Physical workgroups to assist development |  | Security Working Group (SWG) | In Progress | (2) Normal
Support ERO internal controls initiatives (whitepapers, compliance guidance) | With additional members of the OC and PC. |  | Security Working Group (SWG) | In Progress | (2) Normal
Utility Essential Security Practices Whitepaper | Guidance for cyber/physical security protections for non-CIP utility technologies such as inverters, synchro-phasers, natural gas SCADA, etc. (Resources aligned with Electric-Gas Working Group (EGWG) ) |  | Security Working Group (SWG) | In Progress | (2) Normal | Include members with security expertise on Operating Reliability Subcommittee (ORS), Electric-Gas Working Group (EGWG), and possibly others
Attack scenarios on midstream or interstate natural gas pipelines | Joint effort with OC/PC |  | Security Working Group (SWG) | In Progress | (2) Normal | Include members with security expertise on Electric-Gas Working Group (EGWG), Reliability Assessment Subcommittee (RAS) and/or Probabilistic Assessment Working Group (PAWG), with collaboration by E-ISAC
Planning approaches, models and simulation approaches that reduce the number of critical facilities | Joint effort with PC/OC |  | Security Working Group (SWG) | In Progress | (2) Normal | Include members with security expertise on Electric-Gas Working Group (EGWG), Reliability Assessment Subcommittee (RAS) and/or Probabilistic Assessment Working Group (PAWG), with collaboration by E-ISAC
Response to GridEx V lessons learned | Placeholder for anticipated work items stemming from the bi-annual GridEx lessons learned |  | Security Working Group (SWG) | In Progress | (2) Normal | Add members with security expertise to Operating Reliability Subcommittee (ORS)
2021 State of Reliability Report (SOR) | Rules of Procedure Section 800 states that NERC will: “conduct and report the results of an independent assessment of the overall reliability and adequacy of the interconnected North American Bulk Power Systems, both as existing and as planned” and “develop reliability performance benchmarks. The final reliability assessment reports shall be approved by the Board for publication to the electric industry and the general public” *Rules of Procedure -https://www.nerc.com/FilingsOrders/us/RuleOfProcedureDL/NERC_ROP_Effective_20190125.pdf - Section 800 |  | Performance Analysis Subcommittee (PAS) | In Progress | (2) Normal | To be presented to RSTC in June for Endorsement.
Update CIPC remote access guideline | Update remote access guideline taking (as input) the NERC remote access study, filed with FERC in 201x |  | Security Working Group (SWG) | In Progress | (2) Normal
Develop SAR to consolidate Glossary definitions of ACE | Develop SAR to consolidate Glossary definitions of ACE |  | Resources Subcommittee (RS) | In Progress | (2) Normal | This is a continuation of the SAR initiated by T Bilke in 2019
Support the efforts of the BAL-003-1 SDT | Support the efforts of the BAL-003-1 SDT |  | Resources Subcommittee (RS) | In Progress | (2) Normal | In Progress - Is this the same as Item 9?
Determine a more efficient method to collect CPS1, BAAL, and DCS data to eliminate voluntary submittal forms | Determine a more efficient method to collect CPS1, BAAL, and DCS data to eliminate voluntary submittal forms |  | Resources Subcommittee (RS) | In Progress | (2) Normal | This effort is still not fully scoped.
Technical Report on Methods for Analyzing and Mitigating Forced Oscillations | To address potential reliability impacts from forced oscillation events (e.g., January 2019 EI event), SMS will provide guidance on how RC/TOPs can determine the quantities to be monitored, thresholds to be monitored and the corresponding mitigation actions for consistency in developed operating procedures and mitigation plans. |  | Synchronized Measurement Working Group (SMWG) | In Progress | (2) Normal
Modeling and Simulations Technical Report. | Modeling and Simulations Technical Report. Findings, recommendations, and experiences modeling and studying inverter-based resources; information from NERC Alert data collection; generation interconnection studies; IRPTF stability studies |  | Inverter-Based Resource Performance Working Group (IRPWG) | Completed | (2) Normal
Canyon 2 NERC Alert Follow Up | Canyon 2 NERC Alert Follow Up – Modeling and Simulation. Follow up work to ensure accurate and appropriate models are being used for local and interconnection-wide studies and base case creation. Engagement with MOD-032 Designees, Planning Coordinators, Transmission Planners, and Generator Owners to ensure accurate modeling. Follow up with the proposed changes and execution of those changes. |  | Inverter-Based Resource Performance Working Group (IRPWG) | Completed | (2) Normal
Technical Report: Energy Transition to Higher Penetrations of Inverter-Based Resources | Continuation of “Tabled Issues” . Discussion of IRPTF and NERC activities beyond those captured in the PRC-024-2 White Paper, as documented in the white paper. Discussion, analysis, and recommendations for continued improvements to inverter-based resource performance and NERC standards |  | Inverter-Based Resource Performance Working Group (IRPWG) | In Progress | (2) Normal
Reliability Guideline: EMT Modeling and Studies | Positive-sequence models are utilized to represent generator resources in typical dynamic stability tools used by power system engineers in various studies. However, these models contain certain simplifications for inverter-based resources (IBRs) that may lead to erroneous results under certain system conditions (e.g., low system strength). The reliability guideline will provide guidance on when and how an entity should be performing Electromagnetic Transient Modeling (EMT) analysis. This reliability guideline will build off of the previously developed reliability guidelines by IRPTF. |  | Inverter-Based Resource Performance Working Group (IRPWG) | In Progress | (2) Normal
Reliability Guideline: Battery Energy Storage (BESS) and Hybrid Plant Performance and Modeling | Battery storage systems are increasing in size and number. Further, use of hybrid resources is increasing. There is lack of guidance and expertise on how to model and simulate these types of new resources in interconnection studies and planning assessments. The IRPTF will develop a reliability guideline that outlines recommended practices. |  | Inverter-Based Resource Performance Working Group (IRPWG) | In Progress | (2) Normal
Load Composition Analysis (e.g, Buildings, end uses) | Load Composition Analysis (e.g, Buildings, end uses) |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
System Impact Assessment. | System Impact Assessment. Utility members sharing experience of load modeling and studies; user forum for sharing lessons learned. |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
Robust (Default) Data Sets. | Robust (Default) Data Sets. Default datasets to support utilities seeking guidance on reasonable load model parameters (e.g., starting point or no other data available) |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
Modeling Notifications: Composite Load Model Benchmarking. | Modeling Notifications: Composite Load Model Benchmarking. Develop composite load model benchmarking notification to share with industry the completion and usability of the models across all major software platforms. |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
Load Model (Software) Benchmarking | Load Model (Software) Benchmarking |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
Dynamic Load Modeling in Real-Time Stability Analysis. | Dynamic Load Modeling in Real-Time Stability Analysis. Assessment of industry practices for use of dynamic load models for real-time or operations planning studies |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
Progressive Protection System Modeling. | Progressive Protection System Modeling.Testing and studying progressive tripping, reconnection, and stalling modeling approach for improved model performance |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
Improved Single-Phase Motor Model | Improved Single-Phase Motor Model |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
Improved Three-Phase Motor Model | Improved Three-Phase Motor Model |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
Efficient Data Format & Model Management. | Efficient Data Format & Model Management. New data format to modularize dynamic load models |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
Power Electronics Load, adjustable drive (VFD, ECM) electric vehicle charger models | Power Electronics Load, adjustable drive (VFD, ECM) electric vehicle charger models |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
Load Model Data Management Tool | Load Model Data Management Tool |  | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
Scope Review | Perform periodic scope review |  | Probabilistic Assessment Working Group (PAWG) | Completed | (2) Normal | Completed per RSTC approval on PAWG updated Scope doucment.
Educational Material to Support Information Sharing between Industry Stakeholders. | Educational Material to Support Information Sharing between Industry Stakeholders. Develop material to educate industry stakeholders on practices, recommendations and technical work developed by other industry organizations. |  | System Planning Impacts from Distributed Energy Resources Working Group Modeling (SPIDERWG-MODELING) | Abandoned | (2) Normal | Task cancelled; references to industry materials and SPIDERWG materials will be provided in other work products. Ongoing industry outreach and engagement by SPIDERWG members.
Reliability Guideline: DER Data Collection for Modeling. | Reliability Guideline: DER Data Collection for Modeling. Guideline providing recommendations and industry practices for the mandatory and optional DER data to be collected by the Reliability Coordinator as well as on how, where, and when to gather such data. |  | System Planning Impacts from Distributed Energy Resources Working Group Modeling (SPIDERWG-MODELING) | Completed | (2) Normal | Approved by RSTC at October 2020 meeting.
Review of MOD-032-1 for DER Data Collection. | Review of MOD-032-1 for DER Data Collection. (In coordination with activity M4) White paper reviewing MOD-032-1 and providing potential modifications to the standard to facilitate data collection for DERs for interconnection-wide modeling. |  | System Planning Impacts from Distributed Energy Resources Working Group Modeling (SPIDERWG-MODELING) | Completed | (2) Normal | This item was completed with teh white paper approved by PC and the subsequent SAR also endoresed. The SAR then was sent to SC, where it was handled in that committee.
EIDSN Tool Development Monitoring | Monitor development of common tools and act as point of contact for EIDSN |  | Real Time Operating Subcommittee (RTOS) | In Progress | (2) Normal | On-going
Parallel Flow Visualization too | RTOS to act as lead on development of, and recommendation to implement, Parallel Flow Visualization tool |  | Real Time Operating Subcommittee (RTOS) | In Progress | (2) Normal | Q3 2022
Time Monitors | Notify RSTC of Time Monitors for 2022 and 2023 |  | Real Time Operating Subcommittee (RTOS) | In Progress | (2) Normal | Q4 Annually
GMD Monitors | Notify RSTC of changing GMD Monitors |  | Real Time Operating Subcommittee (RTOS) | In Progress | (2) Normal | Q4 Annually
Frequency Monitor Reporting | Frequency Monitor Reporting (Standing RTOS agenda item to discuss) |  | Real Time Operating Subcommittee (RTOS) | In Progress | (2) Normal | On-going
Reliability Guideline: Cyber Intrusion Guide for System Operators | Reliability Guideline: Cyber Intrusion Guide for System Operators (Approved by the Operating Committee on June 5, 2018) |  | Real Time Operating Subcommittee (RTOS) | Not Started | (2) Normal | On-going
Reliability Coordinator Plan Reference Document | Reliability Coordinator Plan Reference Document |  | Real Time Operating Subcommittee (RTOS) | Not Started | (2) Normal | Q4 2021
Reliability Guideline: Gas and Electrical Operational Coordination Considerations | Periodic review of the Reliability Guideline: "Gas and Electrical Operational Coordination Considerations" |  | Real Time Operating Subcommittee (RTOS) | In Progress | (2) Normal | RTOS responded to comments - to approve at May 5 meeting and submit to RSTC for June approval
Conduct annual metric review | Implement annual metric review |  | Performance Analysis Subcommittee (PAS) | Not Started | (2) Normal
CMEP DER Guide | Provide CMEP staff questions to ask regarding their collection and use of DER across the various modeling and TPL standards. |  | System Planning Impacts from Distributed Energy Resources Working Group Modeling (SPIDERWG-MODELING) | In Progress | (2) Normal
SAR PRC-025-2 Hybrid Plants | The SPCWG will be working on understanding the issue with calculating pick up setting for dispersed generation resources. For example, one issue is the addition of energy storage which increases the plant total MVA. Protection system loadability is determined by nameplate MVA; however, in the case of storage the energy is not technically seen by the relays depending on how the plant is setup to operate. The standard calls for using the gross aggregate nameplate and may result in a loadability setting with too great of a margin, thus impacting cooridation, dependability, and/or security.​ |  | System Protection and Control Working Group (SPCWG) | In Progress | (2) Normal | Technical aspects will be discussed at the June SPCWG meeting.
CMLD Deployment (Phase2)-1 | Dynamic load model is implemented, tested and benchmarked in all production grid simulators - Siemens PTI PSS®E, General Electric PSLF, PowerWorld, and PowerTech TSAT | 2019-03-31 | Load Modeling Working Group (LMWG) | Completed | (2) Normal | COMPLETED - Phase 1 of the model benchmarking is completed successfully in PTI PSS®E, GE PSLF, PowerWorld, and PowerTech TSAT
CMLD Deployment (Phase1)-01B | DER Models are implemented, tested and benchmarked as a part of the dynamic load model | 2019-06-30 | Load Modeling Working Group (LMWG) | Completed | (1) High | COMPLETED - Benchmarked DER Implementation, coordinated with SPIDER on DER modeling for dynamic load model, ensure that SPRIDER-develop models and data sets are updated in Load Model Data Tool
CMLD Deployment (Phase1)-02 | Load Model Data | 2019-06-30 | Load Modeling Working Group (LMWG) | Completed | (1) High | Complete
CMLD Deployment (Phase1)-02A | Mapping between powerflow Loads and "Load Type" Identifiers | 2019-06-30 | Load Modeling Working Group (LMWG) | Completed | (1) High | COMPLETED - NERC Regions identified load climate<br>zones (airport codes) and corresponding "Load Type" identifiers, NERC Regions worked with Transmission Planners to develop mapping between power flow load buses and "Load Type" identifiers
CMLD Deployment (Phase1)-02B | Load Composition Data Sets Developed | 2019-06-30 | Load Modeling Working Group (LMWG) | Completed | (1) High | COMPLETED - NERC LMTF worked with DOE to develop 24-hour Load Composition Data Sets for 96 airport codes in NERC footprint for three seasons.
CMLD Deployment (Phase1)-02C | Model Data for Large Industrial Loads | 2019-06-30 | Load Modeling Working Group (LMWG) | Completed | (1) High | COMPLETED - NERC LMTF engaged industry experts to develop representative data sets for 20 types of industrial loads
CMLD Deployment (Phase1)-02D | Robust Data Sets - End Use Data | 2019-06-30 | Load Modeling Working Group (LMWG) | Completed | (1) High | COMPLETED - Model data sets are developed based on extensive end-use testing and manufacturer's literature The data is stress-tested in PTI PSS®E and GE PSLF
CMLD Deployment (Phase1)-03 | Tools for Load Model Data management | 2019-06-30 | Load Modeling Working Group (LMWG) | Completed | (1) High | COMPLETED - NERC Developed Load Model Data Tool for managing load model data and writing CMLD records in PTI PSS®E DYR and GE PSLF DYD formats. The tools are used to generate CMLD records for the field test and provided to NERC Regions
Support the ERSWG Measures 1, 2, 4, and 6 concerning BAL-003 | ​Support the ERSWG Measures 1, 2, 4, and 6 as much a practicably possible and the full implementation of BAL-003-1. | 2019-09-30 | Resources Subcommittee (RS) | Completed | (2) Normal | ​Support of the existing measures is already in place and ongoing (each measure is reviewed for each interconnection at each RS meeting). A sub-team has been established (led by Brad Gordon) to modify/develop ERS sub-measures and improved metrics. The due
EMS Functions - Risks and Mitigations | Develop a reference document regarding how to lessen and mitigate risks for losing EMS functions.​ | 2020-03-03 | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | ​Kick off 3rd quarter 2020.
Review the UK final report for findings and recommendation’s that are applicable to the North American grid and present to the OC | Review the UK final report for findings and recommendation’s that are applicable to the North American grid and present to the OC | 2020-03-31 | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | Completed. Presented to the RSTC at the March 2020 meeting.
1-2020 Summer Reliability Assessment | Seasonal Reliability Assessment Required by NERC RoP Sect 800. Include seasonal scenarios to evaluate resource/energy adequcy risks in assessment areas. LTRA 2019 Rec 1 | 2020-06-30 | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | Complete. Published in May 2020.
5-Ramping Resource Analysis | Measure 6 Analysis White Paper documenting the results of screening analysis to identify areas with changes in their load patterns or their resource mix that could impact ramping and flexibility needs over time LTRA 2019 Rec 4 | 2020-06-30 | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | Complete. RAS approved white paper documenting results of pilot assessment and posted it on the RAS website. Methods such as the screening approach described in the white paper will be used to evaluate ramping concerns in future assessments.
5-Scope Review | Perform periodic scope review | 2020-06-30 | Probabilistic Assessment Working Group (PAWG) | Completed | (2) Normal | RSTC approval requested in December 2020
Annual Monitoring and Situational Awareness Conference | Plans, arrangements and agenda for Annual Monitoring and Situational Awareness Conference | 2020-09-30 | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | The Monitoring and Situational Awareness Conference was held virtually across three sessions on 9/24, 10/15, and 11/10.
Prepare for and facilitate the Annual Winter Weather Prep Webinar. | Prepare for and facilitate the Annual Winter Weather Prep Webinar. | 2020-09-30 | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | Annual webinar was held on 9/3/2020.
Develop Lessons Learned | Publish Lessons Learned. Prepare and facilitate Lessons Learned webinars. Prepare detailed presentation of event for "training" session before RSTC meetings. | 2020-09-30 | Event Analysis Subcommittee (EAS) | Completed | (2) Normal
Annual review of CERTS/NERC (fnet, etc.) real-time applications. | Annual review of CERTS/NERC (fnet, etc.) real-time applications. | 2020-09-30 | Resources Subcommittee (RS) | In Progress | (2) Normal | Annually
Review and approval of the Annual Frequency Response Analysis Report during Q3 of each year. | Review and approval of the Annual Frequency Response Analysis Report during Q3 of each year. | 2020-09-30 | Frequency Working Group (FWG) | In Progress | (2) Normal | Complete for 2019 - NERC Staff Task, RS approval, OC Endorsement
Generator Survey for Eastern, Western, and HQ Interconnections | Generator Survey for Eastern, Western, and HQ Interconnections | 2020-12-31 | Resources Subcommittee (RS) | In Progress | (2) Normal | ​Approximately two events selected each year for the upcoming years. Conduct Webinars to identify issues and support industry.
1-Review IRPWG Scope | Revised scope with new IRPWG group. | 2020-12-31 | Inverter-Based Resource Performance Working Group (IRPWG) | Completed | (2) Normal | Seeking approval at December 2020 RSTC meeting.
2-San Fernando Disturbance Follow-Up | Discussion of NERC San Fernando Disturbance Report and identification of any next steps for IRPWG to add to work plan. | 2020-12-31 | Inverter-Based Resource Performance Working Group (IRPWG) | In Progress | (2) Normal | IRPWG will meet in November to determine next steps.
2-Long-Term Reliability Assessment | Annual Reliability Assessment Required by NERC RoP Sect 800. Includes probabilistic assessment (ProbA) to assess energy adequacy risk (LTRA Rec 1). Analysis is also underway to assess storage impacts on BPS (LTRA Rec 6)and transmission development trends/reliability risk (LTRA rec 7). LTRA 2019 Rec 1, 6, and 7 | 2020-12-31 | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | RSTC Review Complete. Endorsement vote in progress November 2020.
3-Winter Reliability Assessment | Seasonal Reliability Assessment Required by NERC RoP Sect 800. Include seasonal scenarios to evaluate resource/energy adequcy risks in assessment areas. LTRA 2019 Rec 1 | 2020-12-31 | Reliability Assessment Subcommittee (RAS) | Completed | (2) Normal | RSTC Review Complete. Endorsement vote conducted November 2020. Published November 18.
2-Long-Term Reliability Assessment Enhancement | Develop screening approaches or other probabilistic studies to supplement LTRA in off ProbA years. LTRA 2019 Rec 1 | 2020-12-31 | Probabilistic Assessment Working Group (PAWG) | Completed | (2) Normal | Completed.
3-Probabilistic Assessment - Base Case | Perform biennial ProbA, sensitivity/scenario studies, for the 2020 LTRA LTRA 2019 Rec 1 | 2020-12-31 | Probabilistic Assessment Working Group (PAWG) | Completed | (2) Normal | Base ProbA included in 2020 LTRA.
Annual update to the RSTC of events, cause codes, trends, etc. | Annual update to the RSTC of events, cause codes, trends, etc. | 2020-12-31 | Event Analysis Subcommittee (EAS) | Completed | (2) Normal
Review and vet the Frequency Bias Settings and L10 values; scheduled to be implemented in April of each year. Repeated annual in accordance with the BAL-003-1 standard. | Review and vet the Frequency Bias Settings and L10 values; scheduled to be implemented in April of each year. Repeated annual in accordance with the BAL-003-1 standard. | 2020-12-31 | Frequency Working Group (FWG) | In Progress | (2) Normal | Ongoing
Quarterly review of BA’s control performance. | Quarterly review of BA’s control performance. | 2020-12-31 | Resources Subcommittee (RS) | In Progress | (2) Normal | Ongoing
LMWG January 2021 Meeting | ​Coordinator for LMWG January 2021 Meeting | 2021-01-28 | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
Work Plan | Develop an SWG work plan for 2021 | 2021-02-26 | Security Working Group (SWG) | Completed | (2) Normal
V1-Reliability Guideline: DER Performance and Model Verification | Reliability Guideline covering aggregate DER model verification, including recommended measurement practices, executing model verification activities, model benchmarking, relation to MOD-033 activities, and conversion of data sources for verification. | 2021-03-02 | System Planning Impacts from Distributed Energy Resources Working Group Verification (SPIDERWG-VERIFICATION) | Completed | (1) High | Responded to Q4 2021 comment period. (High priority task for SPIDERWG)
ERATF Team Kickoff | ​The team held the introductions, reviewed the scope, work plan and agreed to review the white paper. | 2021-03-08 | Reliability Security and Technology Committee (RSTC) | Completed | (2) Normal
Final Report on NERC GMD Research Work Plan tasks (FERC Order No. 851) | Final Report on NERC GMD Research Work Plan tasks; . | 2021-03-31 | Geomagnetic Disturbance Task Force (GMDTF) | In Progress | (2) Normal | EPRI project to address research objectives has concluded. All reports have been made publicly available free of charge. Summary Report has been prepared by NERC staff and GMDTF. RSTC will be briefed on the summary report in March 2021. GMDTF can disband
EAS Scope Document Review | ​Update EAS Scope to reflect transformation of the RSTC. | 2021-03-31 | Event Analysis Subcommittee (EAS) | In Progress | (2) Normal | Presnted for approval at RSTC March 2021 meeting.
Scope Document | Develop Scope Document | 2021-03-31 | Security Working Group (SWG) | Completed | (2) Normal
M1-DER Modeling Survey | Perform industry survey of SPIDERWG members regarding use of DER planning models in BPS studies, dynamic load models and DER modeling guidelines. | 2021-06-08 | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (2) Normal | Survey white paper approved by SPIDERWG; plans to share at June RSTC meeting.
S4A-Reliability Guideline: Recommended Approaches for Developing Underfrequency Load Shedding Programs with Increasing DER Penetration | Guidance on how to study UFLS programs and ensure their effectiveness with increasing penetration of DER represented | 2021-06-08 | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (2) Normal | On track. SPIDERWG completed for review. Going to June RSTC for authorization to post.
1-Data collection approaches and recommendations techincal report | Develop a technical report that describes industry approaches and best practices for probabilistic assessment | 2021-06-08 | Probabilistic Assessment Working Group (PAWG) | In Progress | (2) Normal | PAWG responded to RAS comments from RAS commenting period. Going to RSTC to request RSTC reviewers.
4-Probabilistic Assessment - Scenario Case | Develop and present findings in a Scenario report that expands upon the Base Case LTRA 2019 Rec 1 | 2021-06-09 | Probabilistic Assessment Working Group (PAWG) | In Progress | (2) Normal | Heading to RSTC June meeting for approval.
EGWG - Reliability Guideline Metrics | ​Develop a method to measure the Fuel Assurance Reliability Guideline effectiveness including the following goals set forth for 2021Run metrics and analysis around design basis for potential TPL 001 enhancements;Complete surveys and measurement criteria and results to determine efficacy of Fuel Assurance Guideline implemented in 2020Provide additional criteria for measuring effectiveness of 2017 Guideline: Gas and Electrical Operational ConsiderationsDevelop a summary of effectiveness of guidelines results that can be used to the purposes of SAR(s) or enhancements to existing guidelinesMonitor effectiveness of new GADS cause codes that provide for more visibility into root cause analysis of gas generator outages due to lack of fuel | 2021-06-30 | Electric Gas Working Group (EGWG) | In Progress | (2) Normal | EGWG is holding monthly meetings and making progress on developing a survey as a measurement tool.
5-White Paper: BPS-Connected IBR and Hybrid Plant Capabilities for Frequency Response | White paper on utilizing the full capabilities of inverter-based resources and hybrid plants for providing frequency response. | 2021-06-30 | Inverter-Based Resource Performance Working Group (IRPWG) | In Progress | (2) Normal | New task; on track.
1- 2021 Summer Reliability Assessment | Seasonal Reliability Assessment Required by NERC RoP Sect 800. | 2021-06-30 | Reliability Assessment Subcommittee (RAS) | In Progress | (2) Normal | Report recieved RAS feedback and comments are being addressed. Report is currently being reviewed by the RSTC.
4-Composite Study (Review) | Review and provide input to NERC Staff (Advanced System Analytics and Modeling) on NERC Study of Resource Adequacy and Transmission Deliverability | 2021-06-30 | Reliability Assessment Subcommittee (RAS) | In Progress | (2) Normal | NERC Staff is studying this issue and working with RAS for industry technical input. RAS and PAWG have provided feedback to NERC on study scope.&nbsp; NERC staff and study participants are reviewing results.
Develop EA Chapter of the State of 2021 Reliability Report | Develop EA Chapter of the State of 2021 Reliability Report in coordination with PAS. | 2021-06-30 | Event Analysis Subcommittee (EAS) | In Progress | (2) Normal
Complete Assessing and Reducing Risks Tool | Update tool and support document based on 45-day commenting from industry, deliver for final approval | 2021-06-30 | Security Working Group (SWG) | In Progress | (2) Normal | Industry comments received, document modified as appropriate, scheduled for RSTC vote at June 2021 meeting
Complete Encryption in the Cloud Compliance Implementation Document | Complete changes to document based on RSTC feedback | 2021-06-30 | Security Working Group (SWG) | Not Started | (2) Normal
Lessons Learned - BCSI in the Cloud Tabletop | Lessons learned and supporting documentation from WAPA/Microsoft Azure BCSI in the Cloud Tabletop project | 2021-06-30 | Security Working Group (SWG) | In Progress | (2) Normal | The mock CIP audit of the participant's environment and security controls is complete. The results and relevant observations will comprise the lessons learned document.
FERC CIP Lessons Learned from Commission-Led CIP Reliability Audits, CIP-002-5.1a R1 Att 1 Criteria 2.5 | Action to ensure FERC CIP Lessons Learned and determine if deliverable needed, e.g. white paper, SAR, etc. Researching existing guidance is also part of this activity. | 2021-06-30 | Security Working Group (SWG) | Not Started | (2) Normal
V2-Reliability Guideline: DER Forecasting Practices and Relationship to DER Modeling for Reliability Studies | Guidance providing how forecasting practices are linked to DER modeling for reliability studies. DER forecasting practices are important for accurately representing the correct amount and type of DER, particularly at an aggregate level representation for BPS studies. | 2021-09-14 | System Planning Impacts from Distributed Energy Resources Working Group Verification (SPIDERWG-VERIFICATION) | In Progress | (2) Normal | Nearing completion of SPIDERWG review. Planned to request approval to post for industry comment in Q2 2021 RSTC meeting.
S2a-SAR: Updates to TPL-001 Regarding DER Considerations | Sub-team is developing a SAR that incorporates the recommendations put forth in the approved white paper, considering the items that need standards revisions to improve reliability. This activity will also be coordinated with IRPWG to address the issues identified in their recently approved white paper identifying issues with TPL-001. | 2021-09-14 | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (1) High | RSTC did not approve SAR presented at March 2021 RSTC meeting; sub-group responding to comments from RSTC members with plan of bring back updated draft.
O1-White Paper: FERC Order 2222 and BPS Reliability Perspectives | White paper identifying key BPS reliability perspectives with the recently released FERC Order 2222. Being developed by SPIDERG sub-group leadership and Dan Kopin, and will get full review and input from overall SPIDERWG once initial draft complete. | 2021-09-14 | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (1) High | Deadline bumped back to Q3; SPIDERWG volutneers added to team to draft responses to comments received.
CMLD Deployment (Phase1)-05A | Field Test Report | 2021-09-30 | Load Modeling Working Group (LMWG) | In Progress | (1) High | NERC LMWG to develop the field test report for RSTC approval, Update the Reference Document (task 5 is a pre-requisite)
CMLD Deployment (Phase2)-10 | Improvements to three-phase motor models | 2021-09-30 | Load Modeling Working Group (LMWG) | In Progress | (1) High | GE PSLF implemented better three-phase motor models. The next step is to compare the model against the existing model to make the determination whether to proceed with it in all other programs (task 7 is pre-requisite). NERC LMWG found issues with frequen
8-Reliability Guideline: Recommended Approach to Interconnection Studies for BPS-Connected Inverter-Based Resources | Focused guidance on improving the study process for BPS-connected inverter-based resources, particularly with increasing penetrations of these resources and the growing complexity of performing sufficient studies to ensure BPS reliability. | 2021-09-30 | Inverter-Based Resource Performance Working Group (IRPWG) | In Progress | (2) Normal | New task, on track
7-2021 Probabilistic Analysis Forum | Plan and enact a 2021 Probabilistic Analysis Forum (PAF) akin to the 2019 PAF. | 2021-10-05 | Probabilistic Assessment Working Group (PAWG) | In Progress | (2) Normal | Ongoing; Call for abstracts and save the date release in June.
3- 2021-2022 Winter Reliability Assessment | ​Seasonal Reliability Assessment Required by NERC RoP Sect 800. | 2021-11-30 | Reliability Assessment Subcommittee (RAS) | Not Started | (2) Normal | Planning begins in June.
2- 2021 Long Term Reliability Assessment | ​Annual Reliability Assessment Required by NERC RoP Sect 800. | 2021-12-09 | Reliability Assessment Subcommittee (RAS) | In Progress | (2) Normal | Regional Entity and Assessment Area Input Request is In Development
S1-Reliability Guideline: Bulk Power System Planning under Increasing Penetration of Distributed Energy Resources | Reliability Guideline providing recommended practices for performing planning studies considering the impacts of aggregate DER behavior – study approaches, analyzing BPS performance criteria incorporating DER models into studies, developing study assumptions, etc. | 2021-12-14 | System Planning Impacts from Distributed Energy Resources Working Group Studies (SPIDERWG-STUDIES) | In Progress | (1) High | On track; nearing completion of initial draft, compiling the many differing sections. Lowered priority from previous work plans.
S3-Recommended Simulation Improvements and Techniques | Develop and provide guidance to software vendors on simulation improvements on DER. | 2021-12-14 | System Planning Impacts from Distributed Energy Resources Working Group Studies (SPIDERWG-STUDIES) | In Progress | (1) High | On track; vendor engagement in near future
S4B-White Paper: DER Impacts to UVLS Programs | Short white paper on potential impacts of DERs on UVLS program design; leverage work of PRC-010 standards review (C6 task). | 2021-12-14 | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (2) Normal | On track.
C6-NERC Reliability Standards Review White Paper | White Paper reviewing NERC Reliability Standards and impacts of DER. | 2021-12-14 | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (1) High | On track; initial reviews complete, consolidating responses into draft white paper; white paper in review by SPIDERWG subgroup. Needs SPIDERWG review and RSTC review prior to approval.
Section 1600 Data Request for GADS | NERC RoP GADS Section 1600 Data Reporting to collect and analyze GADS data: • Conventional - relevant design data and enhanced event reporting • Wind - connected energy storage and event reporting • Solar - plant configuration, performance and event data as well as equipment outage detail | 2021-12-15 | Performance Analysis Subcommittee (PAS) | In Progress | (2) Normal | To be presented to RSTC in June for acceptance to begin public comment period.
CMLD Deployment (Phase2)-07 | Dynamic Load model for Real-Time Transient Stability Assessment | 2021-12-31 | Load Modeling Working Group (LMWG) | In Progress | (2) Normal | NERC LMWG reached out to PowerTech Labs and RC West on testing load model in TSAT for real-time studies
CMLD Deployment (Phase2)-08 | Modular implementation of the dynamic load model | 2021-12-31 | Load Modeling Working Group (LMWG) | In Progress | (1) High | GE PSLF and PowerWorld aready implemented dynamic load models in their software packages. PTI PSS®E will require the next release of the software - Version 35.
CMLD Deployment (Phase2)-09 | Improvements to single-phase motor models | 2021-12-31 | Load Modeling Working Group (LMWG) | In Progress | (1) High | GE PSLF implemented dynamic phasor models of single-phase motor models. The next step is to compare the model against the existing performance model to make the determination whether to proceed with dynamic phasor model in all other programs (task 8 is a
CMLD Deployment (Phase2)-11 | Improved protection and control models - progressive tripping | 2021-12-31 | Load Modeling Working Group (LMWG) | In Progress | (2) Normal | GE PSLF implemented a motor model version with progressive tripping. The next step is to test the model to make the determination whether to proceed with it in all other programs (task 8 is pre-requisite)
CMLD Deployment (Phase2)-12 | Power Electronic Loads | 2021-12-31 | Load Modeling Working Group (LMWG) | In Progress | (2) Normal | EPRI and BPA tested a number of VFD, ECM drives, as well as charging loads. EPRI is working on more detailed models. The next step is to develop and implement the model in GE PSLF, and compare the model against the existing model to make the determinatio
CMLD Deployment (Phase2)-16 | Transient Voltage Response Criteria | 2021-12-31 | Load Modeling Working Group (LMWG) | In Progress | (1) High | Coordinate with LMWG members and ascertain their inputs and provide guidance on transient voltage response criteria that is required under TPL-001-4 R5
SITES Industry Workshop | SITES will hold an industry-wide technical workshop (likely remotely) to highlight strategic areas of focus related to new technologies, technology enablement, and security integration. (Scope Activity Technology Enablement #2) | 2021-12-31 | Security Integration and Technology Enablement Subcommittee (SITES) | In Progress | (2) Normal | Initial work plan item for team consideration.
Reliability / Security Guideline: Integration of Cyber and Physical Security with BPS Planning, Operations, Design, and System Restoration | Recommendations for industry regarding ways that BPS planning, operations, design, and restoration activities can be enhanced by considering cyber and physical security aspects to improve BPS reliability and resilience; recommendations regarding the convergence of IT and OT networks. (Scope Activity Security Integration #1 and #2) | 2021-12-31 | Security Integration and Technology Enablement Subcommittee (SITES) | In Progress | (2) Normal | Initial work plan item for team consideration.
White Paper: Review and Enhancement of Cybersecurity Maturity Metrics | Review and enhancement of metrics to track the capabilities and maturity of cybersecurity and its integration with BPS reliable operation on a broad level; considerations at a macro-scale, integrating all aspects of overall BPS security, reliability, and resilience. (Scope Activity Security Integration #3 and #5) | 2021-12-31 | Security Integration and Technology Enablement Subcommittee (SITES) | In Progress | (2) Normal | Initial work plan item for team consideration.
White Paper: Risk-Based Physical and Cybersecurity Threats and their Impacts to BPS Reliability and Resilience | Guidance and reference materials providing information about possible security threats and ways that Registered Entities can plan, design, and operate the system to mitigate these potential risks. High-level recommendations for industry to consider in their own engineering and security practices for mitigating potential BPS reliability risks. Considerations for generation, transmission, and distribution-level risks as well as such as the natural gas infrastructure, and end-use (Scope Activity Security Integration #4) | 2021-12-31 | Security Integration and Technology Enablement Subcommittee (SITES) | In Progress | (2) Normal | Initial work plan item for team consideration.
SITES Coordination Activities | Ongoing coordination with other RSTC technical groups to avoid any overlap or duplication; engagement with external stakeholders and industry groups to gather information and share SITES developments; coordination with E-ISAC, ESCC, IEEE, NATF, NAGF, EPRI, and other technical groups. (Scope Activity Coordination #1, #2, #3, and #4) | 2021-12-31 | Security Integration and Technology Enablement Subcommittee (SITES) | In Progress | (2) Normal | Initial work plan item for team consideration.
Develop Lessons Learned in 2021 | Publish Lessons Learned. Prepare and facilitate Lessons Learned webinars. Prepare detailed presentation of event for "training" session before RSTC meetings. | 2021-12-31 | Event Analysis Subcommittee (EAS) | In Progress | (2) Normal | Eight lesson learned have been published in 2021; A lesson learned summary presentation for published lesson learned&nbsp; will be developed and provided in all 20; RSTC agendas.&nbsp; A lesson learned webinars will be conducted as needed
Analysis of cause codes looking for common threads and trends. | Analysis of cause codes looking for common threads and trends. Provide update to RSTC on trends, threads, etc. as required | 2021-12-31 | Event Analysis Subcommittee (EAS) | In Progress | (2) Normal
Events Analysis Program Review and Update | Events Analysis Program Review and Update | 2021-12-31 | Event Analysis Subcommittee (EAS) | In Progress | (2) Normal
Develop Lessons Learned Webinars | Publish Lessons Learned. Prepare and facilitate Lessons Learned webinars. Prepare detailed presentation of event for "training" session before RSTC meetings. | 2021-12-31 | Event Analysis Subcommittee (EAS) | In Progress | (2) Normal
Coordinated Review of NERC Reliability Standards | Develop a technical report outlining a roadmap to ensuring BPS reliability under increasing penetration of inverter-based resources; discussion of issues and possible solutions to these issues. | 2021-12-31 | Inverter-Based Resource Performance Working Group (IRPWG) | Completed | (2) Normal | Completed in 2020 by IRPTF
Transient Voltage Recovery (TVR) and Voltage Dip Criteria | LMWG TVR Task Force to develop Transient Voltage Recovery (TVR) and Voltage Dip Criteria | 2021-12-31 | Load Modeling Working Group (LMWG) | In Progress | (2) Normal
Energy Reliability Assessment Task Force (ERATF) | The task force will look atenergy availability concerns related to operations, operations planning and mid-to-long-term planning horizons. The scope and work plan will be created and sent to the RSTC. | 2021-12-31 | Energy Reliablity Assessment Task Force (ERATF) | In Progress | (2) Normal
Failure Modes and Mechanism Diagrams | ​Development of Failure Modes and Mechanism Diagrams supporting the EA Program's Addendum for Events with Failed Station Equipment. | 2021-12-31 | Event Analysis Subcommittee (EAS) | In Progress | (2) Normal
EMS Special Asssessment | ​EMS Special Asssessment | 2021-12-31 | Event Analysis Subcommittee (EAS) | Completed | (2) Normal | Presented to and endorsed by RSTC March 2020.
Develop external website organization and content | Develop organization and content for the SWG external website (new) along with process for publishing (including approvals). This includes leveraging tools to collect input from industry. | 2021-12-31 | Security Working Group (SWG) | Not Started | (2) Normal
Gas-Electric Planning Basis (N-1) | Develop information that will inform work to create a Reliability Standard for natural gas planning criteria.​ | 2021-12-31 | Electric Gas Working Group (EGWG) | In Progress | (2) Normal | EGWG had their kick off meeting on March 31, 2021. They are seeking comments via the EGWG Extranet.
EGWG - Support of ERATF work plan items around | Develop a plan for looking at long term fuel contracts and how they should be used to ensure fuel availability; how should gas pipeline disruption scenarios be modeled | 2021-12-31 | Electric Gas Working Group (EGWG) | Not Started | (2) Normal | Just announced to the EGWG with plans for a sub-group to address
M6-Modeling Distributed Energy Storage and Multiple Types of DERs | SPIDERWG will dig into technical considerations of modeling distributed energy storage, specifically distributed battery energy storage (D-BESS). The group will also consider how to model multiple types of DERs, including D-BESS and distributed solar PV (D-PV). Lastly, the group will focus on forecasting and dispatch assumptions for D-BESS. SPIDERWG will determine the level of guidance or reference materials needed once discussions begin. Task to be coordinated with Studies sub-group. | 2022-03-15 | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (1) High | Subgroup setup to begin drafting. Bumped to provide seemless RSTC meetings.
S5-White Paper: Beyond Positive Sequence RMS Simulations for High DER Penetration Conditions | Considerations for high penetration DER systems and the need for more advanced tools (e.g., co-simulation tools) for studying DER impacts on the BPS. | 2022-03-15 | System Planning Impacts from Distributed Energy Resources (SPIDERWG) | In Progress | (2) Normal | On track. Draft nearing completion
State of Technology Report | Technical report providing industry with strategic guidance regarding new or emerging technology solutions and risk-based considerations for their successful implementation. (Scope Activity Technology Enablement #1) | 2022-03-31 | Security Integration and Technology Enablement Subcommittee (SITES) | In Progress | (2) Normal | Initial work plan item for team consideration.
Expand Membership | Solicit additional membership and recruit subject matter experts for future projects | 2022-06-30 | Security Working Group (SWG) | In Progress | (2) Normal
CIP Evidence Request Tool Improvements | SWG Evidence Request Tool (ERT) sub-team reviews current and draft versions of the ERT and submits feedback and recommendations to ERO Compliance. | 2022-06-30 | Security Working Group (SWG) | In Progress | (2) Normal | Ongoing interface with ERO Compliance
SWG Processes/Procedures | Develop and implement procedures for project requests, deliverable reviews, roles/responsibilities, website collaboration, scope and work plan reviews, document templates, organizing meetings, and training that will help sustain the SWG | 2022-06-30 | Security Working Group (SWG) | Not Started | (2) Normal
Vetting for BASS & EPG Applications | Ongoing administrative review of user requests. | 2023-07-23 | Resources Subcommittee (RS) | Not Started | (2) Normal